## planning
FISA PLAN4ARI
PIANO IMPEGNO ORE/UOMO COMAU PER WP/TASK
RF= fundamendal research
RI = industrial research
SS = experimental development |  |  |  |  | ANNO I | [11 empty] | ANNO 2 | [11 empty] | ANNO 3 | [11 empty] | ANNO 4
[5 empty] | SEM 1 | [5 empty] | SEM 2 | [5 empty] | SEM 3 | [5 empty] | SEM 4 | [5 empty] | SEM 5 | [5 empty] | SEM 6 | [5 empty] | SEM 7 | [5 empty] | SEM 8
 | time axis 2026-02-01 to 2030-01-01
WP | PM | Type |  | da Allegato A | time axis 2026-02-01 to 2030-01-01
WP1 |  |  | Scientific, Technical and Project Management
T1.1 |  | OTH | Task 1.1 General Management | M1-M48
T1.2 |  | OTH | Task 1.2 Financial management | M1-M48
T1.3 |  | OTH | Task 1.3 Technical and Risk Coordination | M1-M48
T1.4 |  | OTH | Task 1.4 Project Research Data Management | M1-M48
T1.5 |  | OTH | Task 1.5 Creation of Advisory Board | M1-M48
WP2 |  |  | Low-code programming exploiting generative and deliberative AI | bar: 2026-02-01 to 2029-01-01
T2.1 |  | RF | Task 2.1 Update of the scientific plan with the last state-of-the-art methodologies and tools | M7-M12 | bar: 2026-02-01 to 2026-07-01
T2.2 |  | RF | Task 2.2 PDDL2 Generation for Robotic Tasks with Lightweight LLM from Natural Language | M13-M24 | bar: 2026-08-01 to 2027-09-01
T2.3 |  | RI | Task 2.3 PDDL2 to Behavior Tree Generation with time-variance modeling to integrate variability | M18-M24 | bar: 2027-08-01 to 2028-01-01
T2.4 |  | RI | Task 2.4 Task and Motion Planning Optimization in Digital Twin Environment | M22-M30 | bar: 2027-11-01 to 2028-07-01
T2.5 |  | RI | Task 2.5 Optimal BehaviorTree Execution and Online Replanning | M28-M36 | bar: 2028-05-01 to 2029-05-01
T2.6 |  | RI | Task 2.6 Integration of the Task Planning Framework inside MI.RA/Dexter low-code | M28-M36 | bar: 2027-02-01 to 2029-05-01
T2.7 |  | RI | Task 2.7 Continuous Integration | M13-M36 | bar: 2027-02-01 to 2029-05-01
T2.8 |  | RI | Task 2.8 Benchmarking and Evaluation | M7-M12 | bar: 2026-02-01 to 2027-01-01
WP3 |  |  | Sensing for Context Awareness | bar: 2026-02-01 to 2029-05-01
T3.1 |  | RF | Task 3.1 Update of the scientific plan with the last state-of-the-art methodologies and tools | M1-M6 | bar: 2026-02-01 to 2027-01-01
T3.2 |  | RI | Task 3.2 Radar sensor integration for scene monitoring | M7-M9 | bar: 2026-08-01 to 2027-01-01
T3.3 |  | RI | Task 3.3 Fusion of radar sensor data and camera data | M10-M16 | bar: 2026-11-01 to 2027-07-01
T3.4 |  | RI | Task 3.4 Semantic Segmentation | M17-M24 | bar: 2027-08-01 to 2029-05-01
WP4 |  |  | Local and Global Autonomous Motion Planning | bar: 2026-02-01 to 2029-05-01
T4.1 |  | RF | Task 4.1 Update of the Scientific Plan with the latest State-of-the-Art Methodologies and Tools for Motion Planning | M1-M6 | bar: 2026-02-01 to 2026-07-01
T4.2 |  | RI | Task 4.2 Informed Sample-Based Optimal Motion Planning for teams of mobile manipulators in dynamic environments | M4-M24 | bar: 2026-05-01 to 2028-01-01
T4.3 |  | RI | Task 4.3 Model Predictive Control for Optimal Adaptive Micro-interpolation | M4-M24 | bar: 2026-05-01 to 2028-01-01
T4.4 |  | RI | Task 4.4 Integration of the Motion Planning Framework inside MI.RA/Dexter low-code | M25-M30 | bar: 2028-02-01 to 2028-07-01
T4.5 |  | SS | Task 4.5 Integration of the MPC trajectory micro-interpolator inside the COMAU Core IPC | M31-M36 | bar: 2028-02-01 to 2029-05-01
T4.6 |  | RI | Task 4.6 Continuous Integration | M4-M36 | bar: 2026-05-01 to 2028-07-01
T4.7 |  | RI | Task 4.7 Benchmarking and Evaluation | M1-M6 | bar: 2026-02-01 to 2026-07-01
WP5 |  |  | Neural Robust Motion Control | bar: 2026-02-01 to 2029-05-01
T5.1 |  | RF | Task 5.1 Update of the scientific plan with the last state-of-the-art methodologies and tools | M1-M6 | bar: 2026-02-01 to 2026-07-01
T5.2 |  | RI | Task 5.2 Design of the neural controller with prescribed performance constraint architecture | M4-M30 | bar: 2026-05-01 to 2028-07-01
T5.3 |  | RI | Task 5.3 Integration of the Motion Planning Framework inside the Open IPC | M12-M36 | bar: 2027-02-01 to 2029-05-01
T5.4 |  | RI | Task 5.4 Continuous Integration | M4-M36 | bar: 2026-05-01 to 2029-05-01
T5.5 |  | RI | Task 5.5 Benchmarking and Evaluation | M1-M6 | bar: 2026-02-01 to 2026-07-01
WP6 |  |  | Human-Robot Trustiness Evaluation and Assessment | bar: 2026-02-01 to 2029-05-01
T6.1 |  | RI | T6.1 Subjective Evaluation: Design of the Questionnaire | M7-M9 | bar: 2026-02-01 to 2027-01-01
T6.2 |  | RI | T6.2 Subjective Evaluation: Questionnaire Validation | M10-M16 | bar: 2027-02-01 to 2027-11-01
T6.3 |  | RI | T6.3 Subjective Evaluation: Questionnaire Deployment | M17-M24 | bar: 2027-06-01 to 2028-01-01
T6.4 |  | RI | T6.4 Subjective Evaluation: Evaluation Campaign, dataset creation synthesis | M24-M36 | bar: 2027-08-01 to 2029-05-01
WP7 |  |  | Targeted Demonstrator | bar: 2029-02-01 to 2030-01-01
T7.1 |  | SS | Task 7.1 Picking random objects from a warehouse | M36-M48 | bar: 2029-02-01 to 2030-01-01
T7.2 |  | SS | Task 7.2 Remanufacturing of mechanical components | M36-M48 | bar: 2029-02-01 to 2030-01-01
T7.3 |  | SS | Task 7.3 Welding of plates in huge boat | M36-M48 | bar: 2029-02-01 to 2030-01-01
WP8 |  |  | Communication and Dissemination
T8.1 |  | OTH | Task 8.1 Communication activities | M1-M48
T8.2 |  | OTH | Task 8.2 Dissemination activities | M1-M48
T8.3 |  | OTH | Task 8.3 Market analysis and Exploitation plan | M1-M48
Task 1.1 General Management
Task 1.2 Financial management
Task 1.3 Technical and Risk Coordination
Task 1.4 Project Research Data Management
Task 1.5 Creation of Advisory Board
Task 2.1 Update of the scientific plan with the last state-of-the-art methodologies and tools
Task 2.2 PDDL2 Generation for Robotic Tasks with Lightweight LLM from Natural Language
Task 2.3 PDDL2 to Behavior Tree Generation with time-variance modeling to integrate variability
Task 2.4 Task and Motion Planning Optimization in Digital Twin Environment
Task 2.5 Optimal BehaviorTree Execution and Online Replanning
Task 2.6 Integration of the Task Planning Framework inside MI.RA/Dexter low-code
Task 2.7 Continuous Integration
Task 2.8 Benchmarking and Evaluation
Task 3.1 Update of the scientific plan with the last state-of-the-art methodologies and tools
Task 3.2 Radar sensor integration for scene monitoring
Task 3.3 Fusion of radar sensor data and camera data
Task 3.4 Semantic Segmentation
Task 4.1 Update of the Scientific Plan with the latest State-of-the-Art Methodologies and Tools for Motion Planning
Task 4.2 Informed Sample-Based Optimal Motion Planning for teams of mobile manipulators in dynamic environments [
Task 4.3 Model Predictive Control for Optimal Adaptive Micro-interpolation
Task 4.4 Integration of the Motion Planning Framework inside MI.RA/Dexter low-code
Task 4.5 Integration of the MPC trajectory micro-interpolator inside the COMAU Core IPC
Task 4.6 Continuous Integration
Task 4.7 Benchmarking and Evaluation
Task 5.1 Update of the scientific plan with the last state-of-the-art methodologies and tools
Task 5.2 Design of the neural controller with prescribed performance constraint architecture [
Task 5.3 Integration of the Motion Planning Framework inside the Open IPC
Task 5.4 Continuous Integration
Task 5.5 Benchmarking and Evaluation
T6.1 Subjective Evaluation: Design of the Questionnaire
T6.2 Subjective Evaluation: Questionnaire Validation
T6.3 Subjective Evaluation: Questionnaire Deployment
T6.4 Subjective Evaluation: Evaluation Campaign, dataset creation synthesis
Task 7.1 Picking random objects from a warehouse
Task 7.2 Remanufacturing of mechanical components
Task 7.3 Welding of plates in huge boat
Task 8.1 Communication activities
Task 8.2 Dissemination activities
Task 8.3 Market analysis and Exploitation plan