PLAN4ARI

Planning for Artificial Robotic Intelligence and Beyond

DELIVERABLE D1.1

Project Management, Quality and Coordination Handbook

| Project acronym | Plan4ARI |
| --- | --- |
| Project duration | 48 months |
| Work package/activity | Activity 1 - Scientific, Technical, and Project Management |
| Task basis | Task 1.1 General Management, informed by Tasks 1.2-1.5 |
| Activity period | M1-M48 |
| Suggested delivery point | Initial issue in the project start-up phase; maintained as a living document (confirm) |
| Document status | First Draft - Version 0.2 |
| Lead beneficiary | Affiliation Institution |
| Dissemination level | Restricted |

Version 0.2 | 20 July 2026

Host Institution: COMAU S.p.A.  |  Principal Investigator: Nicola Pedrocchi
Research Organisation / Affiliation Institution: Consiglio Nazionale delle Ricerche

# Document control

## Revision history

| Version | Date | Prepared by | Reviewed by | Description |
| --- | --- | --- | --- | --- |
| 0.1 | 20 July 2026 | Drafting support | Nicola Pedrocchi | Initial outline |
| 0.2 | 20 July 2026 | Drafting support | PI/consortium TBC | Expanded operational handbook with standard management methodologies and templates |
| 1.0 | TBC | TBC | Management approval | Approved first issue |

## Approval record

| Role | Name | Organisation | Approval/date |
| --- | --- | --- | --- |
| Principal Investigator / Coordinator | Nicola Pedrocchi | CNR | TBC |
| Project Manager | Nicola Pedrocchi | CNR | TBC |
| Quality and Risk Manager | Nicola Longo | COMAU | TBC |
| Financial Manager | Pier Raffaele Spena | CNR | TBC |
| Data / Ethics lead | Stefano Mottura | CNR | TBC |

# Contents

1. Purpose, scope, and tailoring principles

2. Project management methodology framework

3. Project context, objectives, and management products

4. Governance, roles, and decision-making

5. Integrated planning and lifecycle management

6. Monitoring, control, and performance reporting

7. Meetings, communication, and stakeholder engagement

8. Quality management and deliverable assurance

9. Risk, opportunity, issue, and dependency management

10. Change, configuration, and decision control

11. Financial, administrative, procurement, and resource management

12. Research data, ethics, privacy, safety, security, and responsible AI

13. Software engineering, repositories, and continuous integration

14. Advisory Board, knowledge, IPR, and exploitation interfaces

15. Learning, improvement, project closure, and handbook maintenance

Annex A. RACI matrix

Annex B. Standard registers and templates

Annex C. Deliverable quality checklist

Annex D. Risk scoring matrix and response guidance

Annex E. Glossary and methodological references

# 1. Purpose, scope, and tailoring principles

This handbook establishes the common governance, planning, monitoring, reporting, quality, risk, change, data, ethics, security, and communication procedures for Plan4ARI. It operationalizes Activity 1 of the Project Description, which covers general management, financial management, technical and risk coordination, research data management, and the creation of an Advisory Board.

The handbook applies to all project participants, staff, fellows, subcontractors, and external experts when they perform project work or handle project information. Contractual documents prevail in the event of a conflict. The final Grant/Funding Agreement, Consortium Agreement, and approved amendments shall be inserted in the document hierarchy once available.

## 1.1 Objectives of the handbook

Provide a single, auditable source of project-management rules and responsibilities.

Ensure that technical, financial, and administrative progress is controlled against an approved baseline.

Protect quality, safety, ethics, data protection, information security, and research integrity.

Enable rapid research and software iteration without losing traceability or management control.

Define proportionate escalation and exception routes so that decisions are taken at the appropriate level.

Support continuous reporting, audit readiness, and transparent communication with the financing institution.

## 1.2 Tailoring and proportionality

Plan4ARI is a 48-month applied research and industrial development project. A purely predictive methodology would be too rigid for rapidly evolving AI and robotics research, while a purely agile methodology would not provide sufficient contractual, financial, and safety control. The project therefore adopts a hybrid model: predictive governance and baselines at project level, rolling-wave planning at activity level, and iterative/agile delivery for research and software development.

| Control level | Planning horizon | Method | Primary evidence |
| --- | --- | --- | --- |
| Project | 48 months | Baseline, management by stages, exception control | Approved work plan, budget, deliverables, milestones |
| Activity / WP | 6–12 months | Rolling-wave planning and stage gates | Activity plan, dependencies, KPI and TRL targets |
| Task/team | 2–6 weeks | Agile iteration, Kanban/Scrum-inspired practices | Backlog, sprint/iteration goal, code/test evidence |
| Daily execution | Current work | Visual flow and action management | Issue tracker, action log, repository history |

No certification claim. The handbook is aligned with recognized practices but does not claim certification or full conformity with ISO, PMI, PRINCE2, or any other proprietary scheme. Only the procedures expressly adopted here are binding after consortium approval.

# 2. Project management methodology framework

The methodology combines the following standards and good practices. Each is used selectively to avoid unnecessary bureaucracy and to focus control on outcomes, evidence, and risk.

| Reference | Purpose in Plan4ARI | Applied elements |
| --- | --- | --- |
| ISO 21502:2020 | Overall project-management concepts and practices | Governance, planning, benefits, scope, schedule, cost, resources, risk, quality, change, information, and closure |
| PMI PMBOK Guide – Eighth Edition | Principles and performance domains | Value focus, tailoring, stakeholders, team, planning, delivery, measurement, and uncertainty |
| PRINCE2 Project Management Version 7 | Governance by stages and exception | Defined roles, product focus, stage gates, tolerances, exception reports, and lessons |
| ISO 9001:2015 / PDCA | Quality-management logic | Plan–Do–Check–Act, controlled information, review, non-conformity, and corrective action |
| ISO 31000:2018 | Risk-management principles and process | Context, identification, analysis, evaluation, treatment, monitoring, and communication |
| Agile Manifesto and lean flow practices | Iterative software and research delivery | Short feedback cycles, prioritized backlogs, demos, retrospectives, and limiting work in progress |
| Earned Value and milestone trend analysis | Objective progress and forecast control | Schedule/cost indices where suitable, evidence-based progress, forecast at completion |
| RACI, RAID and decision logs | Responsibility and traceability | Clear ownership of actions, risks, assumptions, issues, dependencies, and decisions |
| FAIR data principles and GDPR | Research data and personal data management | Findability, accessibility, interoperability, reuse, minimization, lawful processing, and accountability |
| ISO/IEC 27001:2022 and ISO/IEC 42001:2023 | Information security and responsible AI management | Risk-based controls, access management, AI-system inventory, human oversight, and continual improvement |

## 2.1 Core management principles

| Principle | Operational meaning |
| --- | --- |
| Value and outcome focus | Activities are managed against project objectives, KPIs, TRL progression, demonstrator needs and expected impact, not merely completion of effort. |
| Single-point accountability | Each management product, task, deliverable, risk and decision has one accountable owner, even where multiple parties are responsible for execution. |
| Evidence before status | Progress claims require verifiable evidence such as accepted documents, test results, repository releases, datasets, demonstrations or approved decisions. |
| Manage by exception | Teams operate within approved tolerances. Forecast breaches trigger an exception report and escalation rather than silent replanning. |
| Product and acceptance focus | Every output is defined by purpose, owner, acceptance criteria, dependencies, review method and evidence of completion. |
| Proportional control | The level of documentation is proportional to risk, cost, safety relevance, personal-data processing and impact on contractual commitments. |
| Transparency and learning | Problems are surfaced early. The project uses blameless root-cause analysis, corrective action and lessons learned. |
| Human-centric and responsible AI | AI-enabled work is subject to human accountability, data governance, safety, transparency and legal/ethical review. |

# 3. Project context, objectives, and management products

Plan4ARI develops an integrated cognitive robotics architecture spanning low-code natural-language programming, deliberative task planning, context-aware sensing, safe motion planning, neural robust motion control, human-robot trustworthiness assessment, and industrial demonstrators. The Project Description organizes the work into eight activities, with Activity 1 providing management across the full 48-month duration.

## 3.1 Document hierarchy

Applicable law, funding decision, and formal Grant/Funding Agreement, including approved amendments.

Consortium Agreement and partner-specific legal agreements.

Approved Project Description, budget, and time schedule.

This handbook and approved subsidiary plans, including Data Management, Communication/Dissemination, and Exploitation plans.

Approved baselines, stage plans, decisions, changes, and waivers.

Operational procedures, templates, registers, and local work instructions.

## 3.2 Mandatory management products and registers

| Management product | Owner | Minimum content | Review |
| --- | --- | --- | --- |
| Master plan and schedule | Coordinator/Project Manager | Baseline and approved changes | Monthly |
| Deliverable and milestone register | Project Manager | Owner, due date, status, reviewers, evidence | Monthly |
| KPI / benefits register | Technical Coordinator | Definition, baseline, target, source, owner | Quarterly |
| RAID register | Quality & Risk Manager | Risks, assumptions, issues, dependencies | Monthly, critical items ad hoc |
| Action and decision logs | Meeting chair / PMO | Actions, due dates, decisions, and rationale | After each meeting |
| Change register | Project Manager | Requests, impact, decision, and implementation | As needed |
| Quality register | Quality Manager | Reviews, findings, NCRs, CAPAs | Monthly |
| Financial forecast | Financial Manager | Actuals, commitments, forecast, and variance | Quarterly or funder cycle |
| Data asset register | Data Manager | Datasets, owner, sensitivity, location, retention | Quarterly |
| AI system/model register | Responsible AI lead / Technical Coordinator | Purpose, owner, data, risk, version, approval | At creation and release |
| IPR and exploitable results register | Exploitation lead | Background, foreground, ownership, protection, and use | Quarterly |
| Communication/dissemination log | Communication lead | Action, audience, approval, evidence, reach | Monthly |
| Lessons-learned log | Project Manager | Observation, consequence, recommendation, owner | At gates and quarterly |

# 4. Governance, roles, and decision-making

The governance model separates strategic accountability, technical coordination, operational delivery, independent advice and control functions. Formal body names and voting rights shall be reconciled with the final Consortium Agreement. The roles below are proposed as the minimum workable structure.

| Role / body | Principal responsibilities |
| --- | --- |
| Principal Investigator / Coordinator | Overall accountability; representation towards the financing institution; approval of baselines, deliverables, major changes, and escalations; chair of the main management body. |
| Project Management Committee (proposed) | Strategic and contractual decisions; partner coordination; approval of major changes, exceptions, resource reallocations, and cross-activity priorities. |
| Technical Committee | Technical coherence across activities; interface and dependency control; review of methods, architectures, KPIs, TRL evidence, integration readiness, and technical risks. |
| Activity / WP Leaders | Plan and deliver their activity; manage task leaders, resources, quality, risks, dependencies, reporting, and contribution to deliverables. |
| Project Manager / PMO | Maintain plans, registers, reporting calendar, meeting governance, document control, action tracking, and submission logistics. |
| Quality and Risk Manager | Maintain quality and risk processes; coordinate independent reviews, audits, NCR/CAPA, and risk escalation. |
| Financial Manager | Maintain budget control, eligibility evidence, forecasts, co-financing records, partner statements, and audit readiness. |
| Data, Ethics, and Privacy leads | Coordinate DMP, data inventory, consent, privacy, ethics approvals, incidents, dataset-release decisions, and records of processing. |
| Safety and Security leads | Coordinate laboratory/demonstrator risk assessment, safety readiness, cybersecurity, and information security controls. |
| Communication / Exploitation leads | Coordinate public communication, dissemination, market analysis, IPR, and exploitable result management. |
| Advisory Board | Provide independent technical and exploitation advice; challenge assumptions; record recommendations without replacing consortium accountability. |

## 4.1 Role-assignment rules

Each task, deliverable, risk, issue, change and dataset shall have one named Accountable owner.

A person may be both Responsible and Accountable for a small item, but accountability shall not be shared ambiguously.

Consulted stakeholders must be engaged early enough to influence the result; Informed stakeholders receive the approved outcome.

Delegation does not remove accountability. Delegations shall be recorded in writing with scope and duration.

Conflicts of interest shall be declared before participation in procurement, review, recruitment, IP or ethics decisions.

## 4.2 Decision categories and authority

| Decision type | Trigger | Authority | Record |
| --- | --- | --- | --- |
| Operational | Within approved task plan and tolerance | Task/Activity Leader | Action or decision log |
| Technical interface | Affects more than one activity or shared architecture | Technical Committee | Technical decision record |
| Baseline change | Affects scope, deliverable, milestone, budget, KPI or contractual commitment | Management Committee / Coordinator; funder approval where required | Change request and amended baseline |
| Safety, ethics, privacy or security | May create unacceptable risk or non-compliance | Relevant control lead with Coordinator approval | Assessment and formal release/stop decision |
| Emergency stop | Immediate risk to people, assets, data or legal compliance | Any authorised person may stop work; restart by designated authority | Incident record and restart approval |

## 4.3 Decision-making procedure

Standard decision process

1. Define the decision, options, constraints, deadline and accountable decision owner.

2. Collect the minimum evidence, including technical, schedule, cost, risk, safety, ethics, data, IPR and stakeholder impacts as applicable.

3. Consult the roles identified in the RACI matrix and document dissenting views where material.

4. Take the decision at the lowest authorised level. Apply quorum/voting provisions from the Consortium Agreement where relevant.

5. Record the decision, rationale, conditions, owner, implementation date and review trigger in the decision log.

6. Communicate the decision to affected parties and verify implementation.

Proposed service levels. Routine decisions should be resolved within 10 working days; urgent cross-activity decisions within 3 working days; safety, ethics, privacy or security stops are immediate. These targets require consortium confirmation.

# 5. Integrated planning and lifecycle management

Planning is performed from outcomes backwards. Each deliverable, software release, dataset, method, demonstrator capability and management product shall have an owner, acceptance criteria, dependencies, resources, target date and objective evidence. Plans are progressively elaborated as uncertainty decreases.

## 5.1 Work breakdown and product descriptions

The approved activity/task structure is the contractual Work Breakdown Structure (WBS). Activity Leaders shall maintain a supporting WBS dictionary for significant outputs. The dictionary prevents different interpretations of “done”.

| Required product-description field | Instruction |
| --- | --- |
| Identifier and title | Unique code consistent with the deliverable/task/repository naming convention. |
| Purpose and user | Why the output exists and who will use or approve it. |
| Scope / exclusions | What is included and explicitly outside scope. |
| Owner and contributors | One accountable owner and named responsible contributors. |
| Acceptance criteria | Observable and testable conditions, including quality, safety, data and performance criteria. |
| Inputs / dependencies | Required upstream decisions, data, hardware, interfaces and partner contributions. |
| Evidence of completion | Report, test log, release tag, dataset DOI, demonstration record, approval or other artefact. |
| Target date / tolerance | Baseline date, permitted tolerance and escalation threshold. |

## 5.2 Planning cycle

Baseline and rolling-wave planning

1. Establish the contractual baseline from the approved Project Description, budget and time schedule.

2. Before each six-month period, Activity Leaders prepare a rolling-wave plan covering outputs, dependencies, resources, gates and risks.

3. Every month, teams update a 90-day look-ahead with task-level dates, actions and required decisions.

4. For software/research work, teams maintain a prioritised backlog and select work for 2–6 week iterations according to capacity and dependencies.

5. Forecasts are updated using actual progress and evidence. Baseline dates are changed only through the approved change process.

## 5.3 Research and technology stage gates

| Gate | Exit criteria | Minimum evidence |
| --- | --- | --- |
| G0 – Baseline readiness | Problem, objectives, owner, resources, KPI and acceptance criteria agreed | Approved product/task description and initial risk assessment |
| G1 – Scientific-method review | State of the art updated; method selected; feasibility and ethics/data implications reviewed | Method review record and updated plan |
| G2 – Simulation / offline verification | Model or algorithm tested in controlled simulation with reproducible evidence | Test report, code tag, baseline comparison |
| G3 – Laboratory prototype | Prototype operates on representative hardware or experimental setup | Lab test report, safety readiness, issue list |
| G4 – Platform integration | Interfaces, timing, security and regression tests passed in MI.RA/Dexter/Open/Core IPC as applicable | Integration release and acceptance record |
| G5 – Demonstrator readiness | Use-case acceptance criteria, operator procedures, safety, data and contingency plans approved | Demonstrator readiness review |
| G6 – Final validation / handover | KPIs assessed; limitations documented; reproducibility and exploitation package complete | Final validation and handover record |

## 5.4 Agile delivery rules for software and research

The backlog shall contain user/research stories with acceptance criteria, priority, dependencies and an owner.

Prioritisation may use MoSCoW (Must, Should, Could, Won’t for the current period) or value/risk scoring.

Work in progress shall be limited to protect flow and reduce partially completed work.

Each iteration ends with a demonstration or evidence review and a short retrospective.

“Done” requires code review, automated tests where feasible, documentation, repository traceability and no unresolved critical defect.

Safety-critical or real-time control components require additional design review, independent verification and controlled deployment.

# 6. Monitoring, control and performance reporting

Monitoring compares approved plans with objective evidence and current forecasts. The purpose is early decision-making, not retrospective reporting. Progress data shall be consistent across technical, financial and administrative reports.

## 6.1 Reporting cadence and data cut-off

| Cadence | Content | Owner / route | Record |
| --- | --- | --- | --- |
| Weekly | Team progress, blockers, safety/quality concerns, upcoming actions | Task teams | Team board / minutes |
| Monthly | Deliverables, milestones, KPIs, resources, RAID, decisions, dependencies, 90-day look-ahead | Activity Leaders to PMO/Technical Committee | Monthly status report |
| Quarterly | Integrated technical and financial forecast, benefits, quality, data, IPR and communication status | PMO and control leads | Quarterly management dashboard |
| At stage gates | Readiness against exit criteria and evidence | Gate owner / reviewers | Gate review record |
| Funder cycle | Formal technical and financial reporting | Coordinator and Financial Manager | Official report / statement |
| Ad hoc | Critical risk, incident, exception, change or non-conformity | Item owner | Escalation record |

## 6.2 Status and forecast rules

Status date: all reports shall state a common cut-off date.

Progress: report evidence achieved, not effort consumed. “90% complete” is not acceptable without defined remaining work and evidence.

Forecast: provide best current estimate, even where it differs from the baseline.

Variance: explain cause, consequence, recovery action, owner and decision required.

Confidence: significant forecasts should include a confidence level or range where uncertainty is material.

Critical path: identify activities that directly affect contractual milestones or demonstrator readiness.

## 6.3 RAG thresholds and exception management

| Status | Proposed trigger | Required action |
| --- | --- | --- |
| Green | Within approved tolerance; no material threat to acceptance criteria | Manage within team and report routinely |
| Amber | Forecast date/cost deviation of 5–10%, moderate KPI/quality risk, or dependency requires management attention | Recovery plan, named owner and closer monitoring |
| Red | Forecast deviation >10%, missed critical milestone, unacceptable safety/ethics/privacy/security risk, or likely contractual impact | Immediate exception report and management decision |

Threshold approval. Numerical thresholds are proposed defaults. The approved project tolerances shall be inserted after review of the Grant/Funding Agreement, budget rules and consortium risk appetite.

## 6.4 Earned Value and milestone trend analysis

For work packages with stable scope and measurable outputs, the project may use simplified Earned Value Management (EVM). Planned Value (PV) is the authorised budgeted value of scheduled work; Earned Value (EV) is the budgeted value of objectively completed work; Actual Cost (AC) is the recorded cost. EV shall be claimed only against pre-agreed completion rules or weighted milestones.

| Indicator | Formula | Interpretation |
| --- | --- | --- |
| Schedule Variance (SV) | EV – PV | Negative values indicate less work completed than planned. |
| Cost Variance (CV) | EV – AC | Negative values indicate cost overrun for achieved work. |
| Schedule Performance Index (SPI) | EV / PV | Below 1.00 indicates schedule underperformance. |
| Cost Performance Index (CPI) | EV / AC | Below 1.00 indicates cost inefficiency. |
| Estimate at Completion (EAC) | Approved forecast; optionally BAC / CPI | Expected final cost based on current evidence and assumptions. |

Where EVM is not meaningful for exploratory research, milestone trend analysis shall be used: each month the forecast date of each key milestone is plotted against the reporting date. Repeated slippage triggers root-cause analysis and a recovery or change decision.

## 6.5 KPI and benefit measurement

| Required KPI field | Rule |
| --- | --- |
| Definition | Unambiguous formula, unit, population and boundary conditions. |
| Baseline | State-of-the-art comparator or pre-project value. |
| Target and tolerance | Approved threshold and acceptable uncertainty. |
| Measurement method | Test protocol, dataset, equipment, sample size and statistical treatment. |
| Owner | One accountable person for data quality and reporting. |
| Evidence location | Repository, test report or dataset identifier. |
| Frequency | Planned measurement and reporting cadence. |
| Limitations | Known bias, assumptions and conditions under which the result does not generalise. |

# 7. Meetings, communication and stakeholder engagement

Meetings shall exist to make decisions, coordinate dependencies, review evidence or solve problems. Information-only updates should be handled asynchronously where practical. Every formal meeting shall have a chair, agenda, time-box, decision/action record and approved minutes or summary.

## 7.1 Meeting architecture

| Meeting | Minimum cadence | Purpose | Chair |
| --- | --- | --- | --- |
| Task/team stand-up or technical sync | Weekly or as needed | Progress, blockers, next actions | Team lead |
| Activity/WP meeting | Monthly | Plan, outputs, risks, resources, dependencies | Activity Leader |
| Technical Committee | Monthly | Architecture, interfaces, methods, KPIs, integration, and technical risk | PI / Technical Coordinator |
| Project Management Committee | Quarterly and ad hoc | Strategic, contractual, financial, exception, and change decisions | Coordinator |
| Quality/risk review | Monthly or combined | RAID, NCR/CAPA, audit, and review status | Quality & Risk Manager |
| Advisory Board | At least twice per year; TBC | Independent scientific and exploitation challenge | Coordinator / AB Chair |
| Stage-gate / demonstrator readiness review | At planned gates | Evidence-based go / conditional go / no-go decision | Gate authority |

## 7.2 Meeting procedure

Meeting workflow

1. Chair issues agenda, objective, required pre-read, and decision points at least 3 working days in advance for routine meetings.

2. Participants review materials and declare conflicts of interest before the relevant item.

3. Chair confirms decisions, actions, owners, and due dates before closing each agenda item.

4. Minutes or a decision/action summary are circulated within 3 working days.

5. Participants submit factual corrections within 3 working days; silence is treated as acceptance unless the Consortium Agreement requires otherwise.

6. Actions remain open in the action log until evidence of closure is accepted by the owner or chair.

## 7.3 Internal communication rules

| Channel | Use | Control |
| --- | --- | --- |
| Controlled document repository | Approved plans, deliverables, minutes, decisions, templates, and records | Versioned, access-controlled, backed up |
| Issue tracker | Technical tasks, defects, actions, and changes | Owner, priority, status, links to code/tests |
| Email | Formal notifications and external correspondence | Use project subject prefix; archive material decisions |
| Instant messaging | Rapid coordination only | Material decisions transferred to the official log |
| Code/data repositories | Source code, models, data, and release evidence | Role-based access, branching, tags, and audit history |
| Public website/social channels | Approved public communication | Communication lead and IPR/confidentiality review |

## 7.4 Stakeholder management

The Project Manager and Communication Lead shall maintain a stakeholder register. Stakeholders are classified by influence, interest, impact, and required engagement. High-influence/high-interest stakeholders receive active management; high-impact groups such as workers and operators require meaningful participation even where formal influence is limited.

| Stakeholder field | Minimum content |
| --- | --- |
| Stakeholder/group | Name or category, organization, and role. |
| Interest and expected value | Needs, concerns, success criteria, and potential resistance. |
| Influence/impact | Decision power and degree of impact from project outcomes. |
| Engagement objective | Inform, consult, involve, collaborate, or obtain approval. |
| Owner and channel | Relationship owner, frequency, and communication method. |
| Privacy/consent constraints | Rules for contact, interviews, surveys, and publication. |

# 8. Quality management and deliverable assurance

Quality management follows a Plan–Do–Check–Act cycle. Quality is designed into output through clear acceptance criteria, competent execution, peer review, traceable evidence, and corrective action. The review does not transfer accountability away from the author or the Activity Leader.

## 8.1 Quality objectives

Outputs are fit for their intended scientific, industrial, and management purposes.

Claims are accurate, evidence-based, reproducible where applicable, and consistent across documents.

Interfaces between AI, sensing, planning, control, trustworthiness, and demonstrators are controlled.

Deliverables are submitted on time and meet contractual, editorial, data, ethics, safety, security, and IPR requirements.

Defects are detected early, and recurrence is reduced through root-cause analysis and corrective action.

## 8.2 Deliverable lifecycle and internal deadlines

| Relative date | Milestone | Owner/output |
| --- | --- | --- |
| T–45 days | Confirm scope, outline, contributors, reviewers and evidence | Lead author / Activity Leader |
| T–30 days | Complete first integrated draft | Lead author |
| T–21 days | Technical peer review and cross-activity review | Independent reviewers |
| T–14 days | Revised draft and comment-resolution log | Lead author |
| T–10 days | Quality, data, ethics, security, IPR and editorial checks | Control leads / Quality Manager |
| T–7 days | Final draft for management approval | Activity Leader |
| T–3 days | Approved, formatted and submission-ready version | Coordinator / PMO |
| T | Submission and archival | Coordinator / PMO |

## 8.3 Review roles and acceptance criteria

| Role | Review focus |
| --- | --- |
| Lead author | Completeness, integration of contributions, source traceability, and comment resolution. |
| Technical peer reviewer | Scientific/technical correctness, method, evidence, limitations, and reproducibility. |
| Cross-activity reviewer | Interfaces, dependencies, consistency, and reuse across the architecture. |
| Quality reviewer | Conformity with template, acceptance criteria, registers, language, and document control. |
| Data/ethics/privacy/security reviewer | Compliance with applicable controls and approvals. |
| IPR/communication reviewer | Confidentiality, ownership, background/foreground, publication, and dissemination status. |
| Coordinator/approver | Overall fitness for submission and contractual alignment. |

## 8.4 Non-conformity and corrective action

NCR/CAPA process

1. Log the non-conformity with evidence, affected output, requirement, and immediate containment.

2. Classify severity: minor, major, or critical. Critical items include safety, ethics, privacy, security, research integrity, or contractual breaches.

3. Assign an owner and due date; perform root-cause analysis proportionate to severity using methods such as 5 Whys or cause-and-effect analysis.

4. Define correction, corrective action to prevent recurrence, and, where useful, preventive improvement elsewhere.

5. Verify effectiveness using objective evidence before closure.

6. Escalate overdue or repeated major/critical findings to the Management Committee.

# 9. Risk, opportunity, issue and dependency management

Plan4ARI adopts a single RAID process for risks, assumptions, issues and dependencies. Risks are uncertain events or conditions; issues have already occurred; assumptions are planning propositions requiring validation; dependencies are required external or cross-activity inputs. Opportunities are managed with the same discipline as threats.

## 9.1 Risk-management process

ISO 31000-aligned cycle

1. Establish context, objectives, stakeholders, risk appetite and assessment criteria.

2. Identify threats and opportunities using workshops, checklists, lessons, technical reviews, FMEA-style analysis and scenario analysis.

3. Analyse likelihood, impact, proximity, detectability and interdependencies; consider existing controls.

4. Evaluate priority against approved thresholds and identify risks requiring escalation.

5. Select and implement treatment, assign an owner and due date, and define residual risk.

6. Monitor indicators and treatment effectiveness; communicate material changes immediately.

## 9.2 Risk taxonomy

Scientific and technical: method feasibility, performance, compute burden, integration, scalability and technical debt.

Schedule and resources: recruitment, availability of key personnel, procurement, dependencies and competing priorities.

Financial and administrative: cost eligibility, co-financing, audit evidence, forecast error and delayed approvals.

Safety and operational: robot motion, human-robot interaction, test setup, equipment damage and near misses.

Data, ethics and privacy: consent, personal data, bias, dataset rights, withdrawal, public release and research integrity.

Cybersecurity and information security: unauthorised access, vulnerable dependencies, data loss and supply-chain compromise.

Legal, standards and regulatory: AI Act, GDPR, machinery/robot safety rules, IPR and changing standards.

Adoption and impact: user acceptance, trustworthiness, demonstrator relevance, exploitation and market change.

## 9.3 Issue and dependency control

| Item | Rule |
| --- | --- |
| Issue priority P1 | Critical safety/compliance or project-stopping issue. Immediate notification and daily management until contained. |
| Issue priority P2 | Major impact on a milestone, KPI, integration or partner commitment. Owner and recovery plan within 2 working days. |
| Issue priority P3 | Moderate local impact. Managed by Activity Leader and reviewed weekly/monthly. |
| Issue priority P4 | Minor improvement or defect. Managed in normal backlog. |
| Dependency | Record provider, receiver, required date, acceptance criteria, status and fallback. Cross-activity dependencies are reviewed monthly. |
| Assumption | Record validation owner and deadline. Invalidated assumptions become issues, risks or change requests. |

# 10. Change, configuration and decision control

Changes are expected in rapidly evolving AI and robotics research. The objective is not to prevent change but to ensure that scope, schedule, cost, quality, risk, safety, data, IPR and contractual consequences are understood and authorised before implementation.

## 10.1 Change categories

| Category | Example | Approval |
| --- | --- | --- |
| Minor operational change | Task sequencing or implementation detail within tolerance and acceptance criteria | Activity Leader; log if material |
| Technical baseline change | Interface, architecture, algorithm family, data schema or release baseline | Technical Committee |
| Management baseline change | Milestone forecast, resource allocation, KPI method or activity plan outside local tolerance | Management Committee / Coordinator |
| Contractual change | Scope, deliverable, due date, budget, beneficiary responsibility or dissemination level | Coordinator and financing institution as required |
| Emergency change | Immediate safety/security containment | Authorised lead; retrospective review within 2 working days |

## 10.2 Change-control workflow

Change request process

1. Raise a uniquely numbered change request describing the current baseline, proposed change, reason and urgency.

2. Assess impacts on objectives, scope, schedule, cost, resources, KPI/TRL, quality, dependencies, safety, ethics, privacy, security, data, IPR, dissemination and exploitation.

3. Identify options, including “do nothing”, temporary workaround and permanent change, with recommendation and residual risk.

4. Obtain technical review and approval at the correct authority level. Do not implement before approval unless it is an authorised emergency containment.

5. Update affected baselines, plans, repositories, documentation, registers and communications.

6. Verify implementation and close the change with evidence.

## 10.3 Configuration management

Each controlled item shall have a unique identifier, owner, version, status and authoritative storage location.

Baselines are immutable snapshots. New versions supersede but do not overwrite approved records.

Document statuses are DRAFT, IN REVIEW, APPROVED, SUBMITTED/PUBLISHED and SUPERSEDED.

Recommended document naming: P4ARI_<Type>_<ID>_<ShortTitle>_v<major.minor>_<YYYYMMDD>.<ext>.

Major versions change approved content or interfaces; minor versions correct or clarify without changing the baseline intent.

All releases shall link requirements/issues to code, tests, documentation, models and datasets where feasible.

# 11. Financial, administrative, procurement, and resource management

Financial management shall maintain a complete audit trail from the approved budget to the actual cost, including supporting documents, payments, allocations to the activity/research category, and a formal report. Local accounting systems remain authoritative; the project financial forecast provides the integrated management view.

## 11.1 Financial control cycle

Financial management process

1. Establish the partner and project budget baseline by cost category, activity, research category, and funding/co-financing source.

2. Record actual costs, commitments, and person-months using approved local systems and eligible-cost rules.

3. Each quarter, reconcile actuals and commitments with the project forecast and explain variances.

4. Forecast Estimate at Completion by partner/activity and identify under-spend, over-spend, recruitment/procurement delays, and co-financing gaps.

5. Prepare partner financial statements and audit evidence according to the financing institution's timetable and formats.

6. Obtain approvals, submit, archive, and address queries or audit findings.

## 11.2 Minimum supporting evidence

Employment contracts, payroll evidence, time/person-month records, and allocation methodology.

Invoices, purchase orders, tender/quotation evidence, delivery/acceptance records, and payment proof.

Travel authorization, agenda/purpose, tickets, accommodation, and expense evidence.

Equipment inventory, depreciation/allocation calculations, and proof of project use where applicable.

Subcontracting or external-service agreements, selection rationale, conflict-of-interest declarations, and acceptance of outputs.

Co-financing records and evidence that costs are not double-funded.

Audit certificates and correspondence with the financing institution.

## 11.3 Resource and team management

| Process | Minimum practice |
| --- | --- |
| Capacity planning | Activity Leaders compare planned demand with named staff availability and competencies at least quarterly. |
| Onboarding | Provide project objectives, role, handbook, repositories, confidentiality, safety, data and security briefing. |
| Competence | Maintain a competence/training matrix for specialised robotics, AI, safety, ethics, data and software roles. |
| Performance and workload | Monitor delivery, workload, wellbeing and key-person dependency; take corrective action before sustained overload. |
| Continuity | Critical roles identify deputies, documentation and handover arrangements. |
| Offboarding | Transfer records, revoke access, return assets, confirm IP/confidentiality and document handover. |
| Equality and inclusion | Monitor fair participation, recruitment and access to opportunities; address barriers and promote gender equality. |

# 12. Research data, ethics, privacy, safety, security, and responsible AI

These controls are integrated into project management because failures can invalidate research, harm participants, prevent deployment, or create legal and reputational consequences. Detailed procedures may be expanded in the Data Management Plan, ethics protocols, safety files, and security plans.

## 12.1 Research data management

Every dataset shall have an owner, purpose, source, legal/ethical basis, sensitivity classification, storage location, access list, retention period, and release decision.

The Data Management Plan shall be created early and updated when new datasets, processing purposes, risks, or dissemination decisions arise.

Data and metadata should follow FAIR principles where compatible with confidentiality, privacy, safety, IPR, and commercial constraints.

Dataset quality controls shall document provenance, collection conditions, labeling, transformations, missing data, bias, version, and limitations.

Public release requires documented approval covering consent, anonymization, rights, security, IPR, licensing, and re-identification risk.

## 12.2 Human participants, ethics, and privacy

Human-data control process

1. Define the study purpose, participant group, data, sensors, risks, benefits, lawful basis, and responsible organization before collection.

2. Obtain required ethics approval and written informed consent. Participation and withdrawal shall be voluntary and documented.

3. Collect only necessary data; prefer anonymization and use pseudonymization where identity linkage must be retained.

4. Separate identifiers from research data, restrict access, and use secure storage/transfer.

5. Implement withdrawal, correction, and deletion procedures consistent with legal and scientific-record obligations.

6. Assess changes in purpose, sensors, AI models, data sharing or publication before implementation.

7. Record incidents and notify the designated privacy authority/role within the applicable legal timeframe.

## 12.3 Laboratory and demonstrator safety

No robot, mobile manipulator, high-rate controller, or human-robot experiment shall start without an approved risk assessment and test authorization.

Test plans shall define safe state, emergency stop, workspace controls, supervision, operator competence, protective measures, and abort criteria.

Software safety functions and experimental AI functions shall be clearly distinguished from certified safety functions.

Incidents and near misses shall be reported immediately, investigated and closed before equivalent testing resumes.

Demonstrator readiness reviews shall include safety, cybersecurity, privacy, operator briefing, contingency and recovery checks.

## 12.4 Information security and cybersecurity

| Control domain | Minimum control |
| --- | --- |
| Classification | Label information as Public, Internal, Confidential or Restricted; apply handling rules. |
| Access | Least privilege, named accounts, multi-factor authentication where available, periodic access review. |
| Repositories | Approved systems, backup, recovery testing, encryption for sensitive data and controlled sharing. |
| Endpoints and networks | Supported systems, patching, malware protection, segmented test networks, and secure remote access. |
| Dependencies | Approved third-party libraries, vulnerability monitoring, license review, and software bill of materials where feasible. |
| Incidents | Immediate containment, preservation of evidence, notification, recovery, and lessons learned. |
| Business continuity | Critical repositories, licenses, hardware, and services have backup or recovery arrangements. |

## 12.5 Responsible use of AI and generative AI

AI may support literature screening, coding, summarization, drafting, testing, and decision support, but human project roles remain accountable. Material AI-assisted outputs shall be reviewed by a competent person and shall not be treated as authoritative evidence without verification.

Do not enter confidential, personal, export-controlled, security-sensitive, or partner-proprietary information into unapproved external AI services.

Verify factual claims, calculations, references, code, licenses, and safety implications using primary sources or tests.

Record the model/service, version/date, purpose, reviewer, and significant limitations for material AI-assisted outputs.

Use approved datasets and document training/fine-tuning provenance, bias, performance, robustness, and human-oversight measures.

Maintain an AI system/model register and perform risk assessment proportionate to intended use and potential harm.

Ensure compliance with the EU AI Act, GDPR, applicable safety law, and organizational policies as their requirements become applicable.

# 13. Software engineering, repositories, and continuous integration

Software is a principal project output and a dependency across activities. All production-relevant code shall be managed in controlled repositories with traceable review, testing, and release evidence. Local prototypes may use lighter controls until they become shared or safety- or performance-relevant.

## 13.1 Repository and branching rules

Each repository shall contain an owner, README, license status, contribution rules, dependency list, build instructions, test instructions, and release history.

Protected main/release branches require peer review and successful automated checks before merge.

Feature branches or short-lived branches shall reference the relevant issue/task.

Releases shall use immutable tags and semantic or documented versioning; release notes identify changes, limitations, and migration steps.

Credentials, personal data, and confidential datasets shall never be committed to source repositories.

## 13.2 Definition of Done for shared software

| Criterion | Minimum evidence |
| --- | --- |
| Requirements/acceptance | Linked issue or story with accepted criteria. |
| Implementation | Reviewed code and documented interfaces. |
| Testing | Unit/integration/regression results; performance and real-time tests where applicable. |
| Quality | Static analysis, formatting, dependency/license checks as feasible. |
| Security | No known critical vulnerability; secrets scan and risk review for exposed interfaces. |
| Documentation | Build, use, configuration, limitations and troubleshooting. |
| Release | Tag, artifact, release notes, responsible owner, and rollback plan. |
| Integration | Compatibility confirmed with the relevant MI.RA/Dexter, Open IPC, Core IPC, ROS2 or simulation environment. |

## 13.3 Defect and release severity

| Severity | Definition | Release rule |
| --- | --- | --- |
| S1 Critical | Safety, security, data loss, system stop or invalidates core result | Release blocked; immediate escalation |
| S2 Major | Key function fails or performance is materially below acceptance | Release is blocked unless a formal waiver and mitigation are provided |
| S3 Moderate | Workaround exists; limited impact | May release with documented limitation and plan |
| S4 Minor | Cosmetic, documentation or low-impact improvement | Backlog or include if economical |

# 14. Advisory Board, knowledge, IPR, and exploitation interfaces

The Advisory Board is established within the first six months according to the Project Description. It provides independent scrutiny of scientific quality and industrial exploitability. Its advice is recorded and considered, while formal decisions remain with the consortium.

## 14.1 Advisory Board terms of reference

Composition: external academic experts and senior COMAU R&D figures, balanced to cover the project modules and industrial relevance.

Appointment: written invitation, role description, confidentiality, and conflict-of-interest declaration.

Inputs: concise progress package, risks, evidence, open decisions, and questions requiring challenge.

Outputs: written recommendations, priority, responsible consortium owner, and response/closure status.

Independence: members shall not review decisions where a conflict could impair impartiality.

## 14.2 Knowledge and IPR management interface

| Control | Procedure |
| --- | --- |
| Background identification | Record pre-existing software, patents, know-how, data and licences needed for project work. |
| Foreground/results | Record creators, contributing partners, ownership basis, evidence, confidentiality and exploitation potential. |
| Open-source decisions | Review ownership, inbound/outbound licences, dependencies, security, publication timing and business model. |
| Publication review | Check confidentiality, patentability, personal data, third-party rights and partner approval before disclosure. |
| Patent decisions | Use invention disclosure, novelty/patent search, ownership and filing decision before public disclosure. |
| Exploitation handover | For each key result, identify owner, target user/market, maturity, protection, dependencies, next investment and roadmap. |

# 15. Learning, improvement, project closure, and handbook maintenance

Continuous improvement is embedded in retrospectives, quality reviews, risk reviews, stage gates, incidents and Advisory Board feedback. Lessons are useful only when converted into an owner, action and changed practice.

## 15.1 Lessons-learned process

Learning cycle

1. Capture the observation and context as soon as practical.

2. Identify what helped or hindered, the consequence, and the underlying cause.

3. Define a specific recommendation and the work products/processes it affects.

4. Assign an owner and decision date; update templates, plans, controls or training when accepted.

5. At later gates, verify whether the lesson was applied and effective.

## 15.2 Project closure and handover

Confirm acceptance or formal disposition of every deliverable, milestone, KPI, demonstrator, and management product.

Reconcile finances, commitments, assets, co-financing, audit evidence, and outstanding claims.

Close or transfer risks, issues, changes, actions, licenses, repositories, data, ethics obligations, and security access.

Complete final IPR, exploitable results, dissemination, and sustainability plans.

Archive controlled records according to contractual, legal and organisational retention periods.

Prepare a final lessons-learned and benefits-realisation handover, including owners for post-project actions.

## 15.3 Handbook ownership and review

The Project Manager maintains this handbook under the accountability of the Coordinator. It shall be reviewed at least annually and whenever there is a significant contractual amendment, governance change, audit finding, new legal obligation, major incident, material tool change or repeated process failure. Revisions follow the change-control procedure and are communicated to all affected participants.

# Annex A. RACI matrix

The matrix below is a proposed baseline. “A” = Accountable; “R” = Responsible; “C” = Consulted; “I” = Informed. Formal role names and delegations require approval. Each row should retain one primary A.

| Process | Coordinator / PI | Project Manager | Technical Committee | Activity Leader | Control lead |
| --- | --- | --- | --- | --- | --- |
| Project baseline and handbook | A | R | C | C | C |
| Activity planning and delivery | I | C | C | A/R | C |
| Cross-activity architecture | A | C | R | R | C |
| Monthly technical reporting | A | R | C | R | C |
| Deliverable authoring | I | C | C | A/R | C |
| Deliverable quality approval | A | R | C | R | R |
| Risk and opportunity management | A | R | C | R | R |
| Issue and dependency management | I | C | C | A/R | C |
| Change control | A | R | C/R | C | C |
| Financial reporting | A | C | I | R | R (Financial) |
| Data / ethics / privacy | A | C | C | R | R (Data/Ethics) |
| Safety / security release | A | C | C | R | R (Safety/Security) |

| Process | Coordinator / PI | Communication / Exploitation | Advisory Board | Partners / contributors | Financing institution |
| --- | --- | --- | --- | --- | --- |
| Public communication | A | R | C | C | I |
| Scientific dissemination | A | R | C | R | I |
| IPR / exploitable results | A | R | C | R | I |
| Advisory Board operation | A | C | R | I | I |
| Contractual submission | A/R | C | I | C | I/Approves as applicable |
| Major contractual change | A | C | C | C | Approves as applicable |
| Project closure | A | R | C | R | I/Accepts as applicable |

# Annex B. Standard registers and templates

## B.1 Monthly status report

| Field | Content |
| --- | --- |
| Reporting period / status date | [Month / cut-off date] |
| Activity / owner | [Activity and accountable leader] |
| Overall RAG and forecast confidence | [Green/Amber/Red; High/Medium/Low] |
| Achievements and evidence | [Accepted outputs, tests, releases, decisions] |
| Next 90 days | [Planned outputs, gates, dependencies and decisions] |
| Deliverable / milestone status | [Baseline, forecast, variance, recovery] |
| KPI / TRL status | [Measurement, evidence, trend, limitation] |
| Resources and financial forecast | [PMs, actuals, commitments, EAC, variance] |
| Top risks / opportunities / issues | [ID, owner, trend, action, escalation] |
| Dependencies and decisions required | [Provider, due date, consequence] |
| Data, ethics, safety, security, IPR | [Changes, approvals, incidents, actions] |

## B.2 RAID register

| ID | Type | Description / cause–event–effect | Owner | P | I | Score | Response / action | Due | Status |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| R-001 | Risk | [Cause] may lead to [event], resulting in [effect] | [Name] | 1–5 | 1–5 | P×I | [Treatment and contingency] | [Date] | Open |
| A-001 | Assumption | [Assumption and validation method] | [Name] |  |  |  | [Validation action] | [Date] | Open |
| I-001 | Issue | [Observed issue and impact] | [Name] |  |  |  | [Containment / recovery] | [Date] | Open |
| D-001 | Dependency | [Input, provider, receiver, need date] | [Name] |  |  |  | [Fallback / escalation] | [Date] | Open |

## B.3 Action and decision log

| ID | Type | Description / decision and rationale | Owner | Due / date | Status | Evidence / link |
| --- | --- | --- | --- | --- | --- | --- |
| ACT-001 | Action | [Action] | [Name] | [Date] | Open | [Link] |
| DEC-001 | Decision | [Decision, options, rationale, conditions] | [Decision owner] | [Date] | Approved | [Record/link] |

## B.4 Change request

| Field | Required content |
| --- | --- |
| Change ID / requester / date | [Unique ID, person, organisation, date] |
| Baseline item affected | [Scope, task, deliverable, milestone, budget, KPI, interface, release] |
| Current baseline and proposed change | [Before / after] |
| Reason and urgency | [Problem, opportunity, regulatory or technical driver] |
| Impact assessment | [Scope, schedule, cost, resource, quality, KPI/TRL, dependencies, safety, ethics, privacy, security, IPR, communication] |
| Options and recommendation | [Do nothing / workaround / change; recommendation] |
| Approvals | [Technical, financial, control leads and decision authority] |
| Implementation / verification | [Actions, owners, dates, updated baselines, evidence] |

## B.5 Meeting agenda and minutes

| Field | Content |
| --- | --- |
| Meeting / date / chair | [Title, date/time, chair] |
| Objective and required decisions | [Why the meeting is held] |
| Participants / apologies / conflicts | [Names and declared conflicts] |
| Agenda and pre-read | [Items, owner, time-box, links] |
| Discussion summary | [Essential evidence and alternatives only] |
| Decisions | [Decision IDs and rationale] |
| Actions | [Action IDs, owners and due dates] |
| Risks / issues / changes | [New or updated IDs] |
| Next meeting | [Date and expected focus] |

## B.6 Stage-gate review record

| Field | Content |
| --- | --- |
| Gate / output / owner | [G0–G6; output and accountable owner] |
| Entry criteria | [Required inputs and prior approvals] |
| Evidence reviewed | [Reports, releases, tests, datasets, risk and safety records] |
| Criteria result | [Pass / conditional / fail for each criterion] |
| Open conditions | [Action, owner and due date] |
| Decision | [Go / Conditional Go / No-Go / Recycle] |
| Approver and date | [Authority and signed/recorded approval] |

# Annex C. Deliverable quality checklist

| Check area | Acceptance question |
| --- | --- |
| Document control | Title, code, version, date, owner, lead, due date, dissemination level and approvals are correct. |
| Scope and objectives | Purpose, audience, contractual requirement, boundaries and links to other outputs are clear. |
| Content completeness | All promised sections, methods, results, evidence, limitations and conclusions are present. |
| Technical correctness | Claims, equations, references, methods, code/data links and interpretations have been independently reviewed. |
| Traceability | Results trace to tasks, KPIs, tests, releases, datasets, decisions and source records. |
| KPI / TRL evidence | Definitions, baselines, targets, measurement methods, uncertainty and evidence are explicit. |
| Interfaces | Dependencies and contributions from other activities are accurate and acknowledged. |
| Quality and reproducibility | Methods, configurations and data provenance are sufficient to reproduce or understand limitations. |
| Data / ethics / privacy | Approvals, consent, anonymisation, access, retention and publication decisions are addressed. |
| Safety / security | Safety and cybersecurity implications, controls, incidents and limitations are addressed. |
| IPR / confidentiality | Background, ownership, licences, third-party rights, patentability and dissemination status are checked. |
| Responsible AI | AI use, data provenance, human oversight, performance, bias and limitations are described where applicable. |
| Editorial quality | Consistent terminology, figures, tables, numbering, captions, references, accessibility and language. |
| Comment resolution | All review comments are resolved, accepted or formally dispositioned. |
| Approval / archive | Final approval, submission evidence and authoritative archive location are recorded. |

# Annex D. Risk scoring matrix and response guidance

## D.1 Likelihood and impact scales

| Score | Likelihood guidance | Impact guidance |
| --- | --- | --- |
| 1 – Rare | <10% or exceptional | Negligible local effect; no milestone/KPI impact |
| 2 – Unlikely | 10–30% | Minor local rework; within task tolerance |
| 3 – Possible | 31–60% | Moderate cross-task effect; management attention required |
| 4 – Likely | 61–80% | Major milestone, KPI, cost, integration or reputation effect |
| 5 – Almost certain | >80% or recurring | Critical contractual, safety, ethics, privacy, security or project-objective effect |

## D.2 Probability–impact matrix

| P\I | 1 | 2 | 3 | 4 | 5 |
| --- | --- | --- | --- | --- | --- |
| 5 | 5 | 10 | 15 | 20 | 25 |
| 4 | 4 | 8 | 12 | 16 | 20 |
| 3 | 3 | 6 | 9 | 12 | 15 |
| 2 | 2 | 4 | 6 | 8 | 10 |
| 1 | 1 | 2 | 3 | 4 | 5 |

Proposed priority bands: 1–3 low; 4–6 moderate; 8–12 high; 15–25 critical. Safety, legal, ethics, privacy and security risks may require escalation regardless of numerical score.

## D.3 Response strategies

| Threat strategy | Use | Opportunity strategy | Use |
| --- | --- | --- | --- |
| Avoid | Change plan to remove the threat or exposure | Exploit | Act to ensure the opportunity occurs |
| Reduce | Lower likelihood or impact through controls | Enhance | Increase likelihood or benefit |
| Transfer / share | Allocate part of exposure contractually or through insurance/partnering | Share | Partner with a party best able to realise it |
| Accept | Tolerate with monitoring and contingency where within appetite | Accept | Monitor without proactive investment |

# Annex E. Glossary and methodological references

## E.1 Glossary

| Term | Definition |
| --- | --- |
| Accountable (A) | Role that owns the outcome and approves completion. |
| Responsible (R) | Role that performs or coordinates the work. |
| Baseline | Approved reference for scope, schedule, cost, quality or configuration. |
| CAPA | Corrective and Preventive Action; action to remove cause and prevent recurrence. |
| Deliverable | Contractually or internally required output subject to defined acceptance. |
| Dependency | Input or condition required from another task, partner or external source. |
| Issue | Event or condition that has occurred and requires resolution. |
| KPI | Key Performance Indicator with defined baseline, target and measurement method. |
| Milestone | Significant control point or achievement, normally with zero duration. |
| NCR | Non-Conformity Report documenting failure to meet a requirement. |
| RAID | Combined log of Risks, Assumptions, Issues and Dependencies. |
| Risk | Effect of uncertainty on objectives; may be a threat or opportunity. |
| Stage gate | Evidence-based decision point for continuation, conditions or rework. |
| Tolerance | Permitted deviation within which a delegated manager may act without escalation. |
| TRL | Technology Readiness Level used to describe maturity. |

## E.2 Methodological and legal references

| Reference | Use in this handbook |
| --- | --- |
| Plan4ARI Project Description – Allegato 2 | Project details, technical modules and Section E.3 time schedule; especially Tasks 1.1–1.5. |
| ISO 21502:2020 | Project, programme and portfolio management — Guidance on project management. |
| ISO 21500:2021 | Project, programme and portfolio management — Context and concepts. |
| Project Management Institute | PMBOK Guide — Eighth Edition and The Standard for Project Management. |
| PeopleCert | PRINCE2 Project Management Version 7. |
| ISO 9001:2015 | Quality management systems — Requirements. |
| ISO 31000:2018 | Risk management — Guidelines. |
| Agile Manifesto | Manifesto for Agile Software Development and supporting principles. |
| ISO/IEC 27001:2022 | Information security, cybersecurity and privacy protection — Information security management systems — Requirements. |
| ISO/IEC 42001:2023 | Information technology — Artificial intelligence — Management system. |
| Regulation (EU) 2016/679 | General Data Protection Regulation (GDPR). |
| Regulation (EU) 2024/1689 | Artificial Intelligence Act. |
| FAIR Guiding Principles | Findable, Accessible, Interoperable and Reusable research data and metadata. |

Official reference links (accessed July 2026): ISO 21502  |  PMBOK Guide  |  PRINCE2 7  |  ISO 31000  |  ISO 9001  |  ISO/IEC 27001  |  ISO/IEC 42001  |  GDPR  |  EU AI Act  |  Agile Manifesto  |  FAIR principles